The Colorado Health Foundation Linkage Lab:

M&E Plan Activity

Your agency team should work together to develop an M&E plan for the outcomes that you identified in your program or service package logic model.

For these outcomes, use the template on the second page of this handout to articulate:

- The “What”

  - Outcome objectives from your logic model

  - Associated outcome evaluation questions

  - Associated outcome indicators

- The “How,” Where, and “When”

  - Data source(s)

  - Evaluation design and data collection methods

  - Data collection timing/frequency

  - Data analysis methods

- The “Who”

- Responsible parties

Then, address the “Why” by making a communication plan for your outcome evaluation findings, using the template on the third page of this handout.

As your planning time comes to a close, be sure to put your plan on the easel paper so that you can present it to the large group. Select someone from your team to make a brief presentation of the plan.

Outcome M&E Plan Table for ____________________________________________,  Date: _____________________

| 1. Outcome Objective | 2. Outcome Eval. Question(s) | 3. Outcome Indicator(s) | 4. Evaluation Design | 5. Data Source & Collection Methods | 6. Data Collection Timing/Frequency | 7. Data Analysis Methods | 8. Responsible Parties |
| --- | --- | --- | --- | --- | --- | --- | --- |
| EXAMPLE: Decrease of 20% in 30-day hospital readmission by 2017 | By how much do we decrease 30-day hospital re-admission rates? Do we reach our target of a 20% reduction by Dec. 2017? | Rate of 30-day hospital re-admissions | Pre/post with comparison group (each using data from prior 12 months) | -Payer (e.g. health plan) claims data -Hospital discharge data from County Hospital and General Hospital | -Pre data from CY 2016; will be available 5/17 -Post data from CY 2017 and will be available 5/18 | -Inferential statistical analysis with adjustment for multiple influences | -Program Director (oversees) -Data Analyst (conducts analyses) |

Communication Plan for the Outcome Evaluation Findings

| 1. Objective for communication/use of findings | 2. Audience(s) | 3. Information to be shared | 4. Formats/Media | 5. Timing | 6. Responsible Parties |
| --- | --- | --- | --- | --- | --- |
| EXAMPLE: Demonstrate to our new provider partner that our services provide the value that we have promised | Provider lead contact and 4-6 other payer stakeholders | Hospital re-admission rates: pre/post among payer’s clients and a comparison group | -Factsheet (on website and sent via email) -Ppt. presentation to provider stakeholder group | August 2018 for factsheet posting and Ppt. presentation | -Director of Evaluation (oversees materials development) -Director of Development (coordinates meeting with provider) -Data Analyst (prepares content) |